## Dashboard
ARIA BOT - PROJECT USER STORIES TRACKER
Voice Controlled 4-Wheel AI Robot ¦ Scrum ¦ 31 Stories ¦ 5 Sprints ¦ 140 Story Points
SPRINT GOALS AND SUMMARY
Sprint | Goal / Outcome | Timeline | Stories | Story Points
Sprint 1 | Robot assembled and powered on. Pi running with all software installed | Weeks 1-2 | 8 | 22
Sprint 2 | All 4 wheels controlled by Pi commands. All 3 sensors streaming data | Weeks 2-3 | 9 | 33
Sprint 3 | ARIA listens to voice, understands GPT-4 commands, moves and speaks responses | Week 4 | 6 | 32
Sprint 4 | Display shows animated face and live telemetry. All systems running together | Week 5 | 4 | 21
Sprint 5 | Custom PCB designed in EasyEDA and ordered from JLCPCB | Post-Build | 4 | 32
EPICS OVERVIEW
Epic ID | Epic Name | Stories | Story Points | Status
EP-01 | Hardware Assembly | 4 | 12 | Not Started
EP-02 | Raspberry Pi Setup | 4 | 10 | Not Started
EP-03 | Motor Control | 5 | 18 | Not Started
EP-04 | Sensor Integration | 4 | 15 | Not Started
EP-05 | Voice and AI Agent | 6 | 32 | Not Started
EP-06 | Display and Emotions | 4 | 21 | Not Started
EP-07 | PCB Design | 4 | 32 | Not Started

## All Stories
ARIA BOT - ALL USER STORIES
Story ID | Epic | Sprint | Title | As a... | I want to... | So that... | Acceptance Criteria | Priority | Points | Status | Assignee | Notes
Sprint 1 - Goal: Robot assembled and powered on. Pi running with all software installed
US-001 | EP-01 | Sprint 1 | Assemble Robot Chassis | Robot Builder | assemble the 4WD chassis with all 4 motors attached | the robot has a solid physical base for all components | 1. All 4 motors screwed firmly to chassis 2. All 4 wheels attached to motor shafts 3. Chassis stable when picked up 4. Battery holder mounted on underside | High | 3 | To Do |  | Use M3 screws from chassis kit
US-002 | EP-01 | Sprint 1 | Mount Pi and Arduino | Robot Builder | mount Raspberry Pi 4 and Arduino Mega on the top platform | both boards are securely fixed and accessible for wiring | 1. Pi mounted with nylon standoffs 2. Arduino mounted beside Pi 3. Both boards stable during movement 4. Arduino USB port accessible | High | 2 | To Do |  | Use M2.5 nylon standoffs. Pi left Arduino right
US-003 | EP-01 | Sprint 1 | Connect Power System | Robot Builder | wire LiPo battery through buck converters to Pi and Arduino | both boards receive stable 5V power without fluctuation | 1. LiPo 11.1V connected to both LM2596 2. Buck 1 outputs 5.0V verified with multimeter 3. Buck 2 outputs 5.0V verified with multimeter 4. Pi powers on from Buck 1 5. Arduino powers on from Buck 2 6. No excessive heat after 5 minutes | Critical | 5 | To Do |  | Adjust LM2596 trim pot while measuring. 5.0V +/- 0.1V acceptable
US-004 | EP-01 | Sprint 1 | Mount Ultrasonic Sensors | Robot Builder | mount 3 HC-SR04 sensors at front left and right of robot | the robot can detect obstacles in all 3 directions | 1. Front sensor facing forward at bumper height 2. Left sensor at 90 degrees left 3. Right sensor at 90 degrees right 4. All sensors level not tilted 5. Sensor cables reach Arduino pins 22-27 | High | 2 | To Do |  | Use hot glue or cable ties. Height 10-15cm from ground
US-005 | EP-02 | Sprint 1 | Flash Raspberry Pi OS | Developer | flash Raspberry Pi OS 64-bit to the 32GB SD card | the Pi has a working operating system and boots to desktop | 1. RPi Imager downloaded on laptop 2. Raspberry Pi OS 64-bit selected 3. SSH enabled in advanced settings 4. Username aria password aria123 5. SD card flashed without errors 6. Pi boots to desktop on first power-on | Critical | 2 | To Do |  | Use Raspberry Pi Imager v1.8 or newer
US-006 | EP-02 | Sprint 1 | Install Python Dependencies | Developer | install all required Python libraries on the Raspberry Pi | all ARIA software can run without missing module errors | 1. System updated with apt update and upgrade 2. FFmpeg and portaudio19-dev installed 3. openai-whisper installed and importable 4. langchain and langchain-openai installed 5. pyserial sounddevice numpy installed 6. pygame and pyttsx3 installed 7. All imports succeed with zero errors | Critical | 3 | To Do |  | python3 -c 'import whisper, langchain, pygame, serial' to verify
US-007 | EP-02 | Sprint 1 | Configure OpenAI API | Developer | set up and verify the OpenAI API connection | ARIA can send requests to GPT-4 and receive valid responses | 1. OpenAI account created at platform.openai.com 2. API key generated starting with sk- 3. Minimum $5 billing credit added 4. API key stored in aria_brain.py config 5. Test call to gpt-4o-mini returns valid response 6. No authentication errors | Critical | 2 | To Do |  | Cost approximately $0.002 per voice command
US-008 | EP-02 | Sprint 1 | Verify Pi-Arduino Serial Link | Developer | confirm Raspberry Pi can communicate with Arduino via USB serial | Python scripts on the Pi can send and receive data from Arduino | 1. Arduino connected to Pi via USB cable 2. Port detected as /dev/ttyUSB0 or /dev/ttyACM0 3. Python pyserial opens the port without errors 4. Test string sent from Pi received on Arduino Serial Monitor 5. Test string from Arduino received in Python on Pi | High | 3 | To Do |  | Run ls /dev/tty* to find port. Use baud rate 9600
Sprint 2 - Goal: All 4 wheels controlled by Pi commands. All 3 sensors streaming data
US-009 | EP-03 | Sprint 2 | Wire L298N Motor Drivers | Developer | wire both L298N motor drivers to the Arduino Mega and motors | all 4 motors can be individually controlled by Arduino PWM signals | 1. L298N 1: IN1=Pin2 IN2=Pin3 ENA=Pin4 IN3=Pin5 IN4=Pin6 ENB=Pin7 2. L298N 2: IN1=Pin8 IN2=Pin9 ENA=Pin10 IN3=Pin11 IN4=Pin12 ENB=Pin13 3. Front-Left motor to L298N-1 OUT1 and OUT2 4. Rear-Left motor to L298N-1 OUT3 and OUT4 5. Front-Right motor to L298N-2 OUT1 and OUT2 6. Rear-Right motor to L298N-2 OUT3 and OUT4 7. GND of Arduino connected to GND of both L298N boards | Critical | 5 | To Do |  | Missing GND connection is the most common wiring mistake
US-010 | EP-03 | Sprint 2 | Upload Motor Test Code | Developer | upload the motor test sketch to Arduino and verify each wheel spins | each of the 4 wheels spins individually confirming correct wiring | 1. Arduino IDE installed on laptop 2. Motor test sketch uploaded without errors 3. Front-Left wheel spins forward 2 seconds 4. Rear-Left wheel spins forward 2 seconds 5. Front-Right wheel spins forward 2 seconds 6. Rear-Right wheel spins forward 2 seconds 7. All wheels spin in correct direction | Critical | 3 | To Do |  | Swap motor wires on L298N if wheel spins wrong direction
US-011 | EP-03 | Sprint 2 | Full Motor Command System | Developer | upload full Arduino code that accepts serial commands from Pi | Arduino responds to FORWARD BACKWARD LEFT RIGHT STOP SPEED commands | 1. FORWARD moves all 4 wheels forward 2. BACKWARD moves all 4 wheels backward 3. LEFT rotates robot left 4. RIGHT rotates robot right 5. STOP halts all motors immediately 6. SPEED:N updates motor speed 0 to 255 7. Arduino sends OK:COMMAND confirmation after each | Critical | 5 | To Do |  | Test each command via Arduino Serial Monitor before connecting Pi
US-012 | EP-03 | Sprint 2 | Test Motor Commands from Pi | Developer | run the Python motor test script from the Raspberry Pi | the Pi can remotely control all 4 wheels via serial commands | 1. test_motors.py created on Pi 2. FORWARD STOP LEFT STOP RIGHT sequence executes 3. Robot physically moves as commanded 4. No serial timeout errors 5. Commands execute within 500ms of sending | High | 3 | To Do |  | Place robot on a box so wheels spin freely during test
US-013 | EP-03 | Sprint 2 | Smooth Speed Control | Developer | implement speed levels slow normal fast turbo for movement | ARIA can move at different speeds depending on voice command | 1. SPEED:100 sets slow mode 2. SPEED:160 sets normal mode 3. SPEED:200 sets fast mode 4. SPEED:255 sets turbo mode 5. Speed persists until changed 6. Noticeably different between slow and fast | Medium | 2 | To Do |  | Avoid PWM values 0-50 as motors may stall
US-014 | EP-04 | Sprint 2 | Wire HC-SR04 Sensors | Developer | wire all 3 HC-SR04 ultrasonic sensors to the Arduino Mega | the Arduino can read distance measurements from all 3 sensors | 1. Front sensor: TRIG=Pin22 ECHO=Pin23 VCC=5V GND 2. Left sensor: TRIG=Pin24 ECHO=Pin25 VCC=5V GND 3. Right sensor: TRIG=Pin26 ECHO=Pin27 VCC=5V GND 4. All VCC to Arduino 5V rail 5. All GND to Arduino GND rail | High | 3 | To Do |  | Use breadboard to distribute 5V and GND to all 3 sensors
US-015 | EP-04 | Sprint 2 | Sensor Data Streaming | Developer | have the Arduino continuously send sensor readings to the Pi | the Pi always knows the distance to obstacles in 3 directions | 1. Arduino sends SENSOR:F,L,R format every 300ms 2. Pi correctly parses sensor data from serial stream 3. Readings accurate within 2cm tested with ruler 4. No interference between sensors 5. Readings update while motors are running | High | 5 | To Do |  | Trigger sensors sequentially not simultaneously to avoid interference
US-016 | EP-04 | Sprint 2 | Obstacle Avoidance Logic | Developer | have ARIA automatically stop when obstacle is within 20cm | the robot does not crash into walls or furniture while driving | 1. Robot stops if front sensor reads less than 20cm while moving forward 2. ARIA speaks an alert when obstacle detected 3. Display shows ALERT emotion 4. Robot can still turn when front blocked 5. Obstacle check runs continuously while moving 6. 3-reading average prevents false positives | High | 5 | To Do |  | Add obstacle check as separate thread running every 200ms
US-017 | EP-04 | Sprint 2 | Sensor Scan Command | Developer | have ARIA report sensor distances when asked to scan | the user can ask scan the area and get a spoken distance report | 1. SCAN action triggers reading all 3 sensors 2. ARIA speaks Front Xcm Left Xcm Right Xcm 3. Scan completes within 1 second 4. Display shows THINKING emotion during scan | Medium | 2 | To Do |  | Format distances to 1 decimal place for clean speech output
Sprint 3 - Goal: ARIA listens to voice, understands GPT-4 commands, moves and speaks responses
US-018 | EP-05 | Sprint 3 | Set Up Microphone Input | Developer | connect and configure the ReSpeaker 2-Mic HAT for voice capture | ARIA can record clear voice audio from the user | 1. ReSpeaker HAT connected to Pi GPIO header 2. Seeed voicecard driver installed 3. Microphone detected by system 4. Test recording captures voice clearly 5. Works from at least 1 metre distance | Critical | 3 | To Do |  | WAITING: ReSpeaker HAT not yet received
US-019 | EP-05 | Sprint 3 | Integrate Whisper STT | Developer | have Whisper convert recorded audio to text locally on the Pi | ARIA can understand spoken English commands offline | 1. Whisper base model loaded successfully 2. 5-second clip transcribed in under 10 seconds 3. Transcription accuracy above 90% for clear speech 4. Robotics commands transcribed correctly 5. Empty recordings return empty string not crash | Critical | 5 | To Do |  | First load downloads approx 150MB. Use tiny model during testing
US-020 | EP-05 | Sprint 3 | Implement GPT-4 AI Agent | Developer | have GPT-4 interpret voice commands and decide robot actions | ARIA understands natural language and maps it to robot actions | 1. GPT-4o-mini API call succeeds with valid response 2. Response parsed into ACTION DURATION SPEED REPLY fields 3. All movement actions work correctly 4. SCAN triggers sensor scan 5. Questions return ACTION NONE with spoken answer 6. Response time under 3 seconds 7. API errors handled gracefully | Critical | 8 | To Do |  | Test with 20 different command phrasings to verify robustness
US-021 | EP-05 | Sprint 3 | Voice Command Loop | Developer | have ARIA continuously listen understand and act in a loop | the user can give multiple voice commands without restarting | 1. ARIA says Listening before each recording 2. Short recordings skipped gracefully 3. Full cycle: listen - transcribe - GPT4 - execute - speak 4. Ctrl+C cleanly stops robot 5. Errors in one cycle do not crash loop 6. Runs 30 plus minutes without memory issues | High | 5 | To Do |  | Wrap entire loop body in try/except. Log errors to file
US-022 | EP-05 | Sprint 3 | Text-to-Speech Output | Developer | have ARIA speak responses out loud using the connected speaker | the user hears ARIA responses and status updates clearly | 1. Speaker connected to Pi 3.5mm audio jack 2. pyttsx3 speaks text without errors 3. Speech rate set to 155 words per minute 4. Volume audible from 2 metres away 5. ARIA announces startup message 6. ARIA speaks GPT-4 response after each command | High | 3 | To Do |  | WAITING: Mini USB Speaker not yet received
US-023 | EP-05 | Sprint 3 | Wake Word Detection | Developer | have ARIA only respond when I say Hey ARIA first | ARIA does not accidentally respond to background conversation | 1. Wake word Hey ARIA triggers recording 2. Commands without wake word are ignored 3. Response latency after wake word under 500ms 4. False wake rate less than 1 per 10 minutes | Low | 8 | To Do |  | Optional enhancement. Implement after core voice loop works
Sprint 4 - Goal: Display shows animated face and live telemetry. All systems running together
US-024 | EP-06 | Sprint 4 | Connect TFT Display | Developer | connect the 3.5 inch TFT display to the Raspberry Pi via SPI | the display shows content controlled by Python pygame | 1. SPI enabled in raspi-config 2. TFT display correctly wired via SPI pins 3. Display shows solid colour in framebuffer test 4. Pygame renders to /dev/fb1 5. No flickering or corruption | High | 5 | To Do |  | WAITING: TFT Display not yet received
US-025 | EP-06 | Sprint 4 | ARIA Animated Face | Developer | have the display show animated eyes that react to ARIA current state | the robot feels alive and expressive with visual emotional feedback | 1. IDLE: slowly blinking blue eyes 2. LISTENING: wide white eyes 3. THINKING: narrow yellow squinting eyes 4. MOVING: bouncing animated cyan eyes 5. SPEAKING: happy green eyes with smile 6. ALERT: flashing red eyes 7. Smooth 30fps animations | High | 8 | To Do |  | Use pygame circles and arcs. Animate with sine wave for natural movement
US-026 | EP-06 | Sprint 4 | Live Telemetry Display | Developer | have the display show live data alongside the animated face | the user can read robot status at a glance from the screen | 1. Current speed shown on right panel 2. Current direction shown 3. Front sensor distance with green or red colour coding 4. Last command text at bottom 5. Data updates within 500ms of change 6. Text readable from 50cm distance | Medium | 5 | To Do |  | Use /tmp/aria_state.json for inter-process communication
US-027 | EP-06 | Sprint 4 | Run Display and Brain Together | Developer | have aria_display.py and aria_brain.py run simultaneously on the Pi | the display and AI brain work in parallel without interfering | 1. Both processes start from a single launch script 2. Display updates while brain processes voice 3. No lag in either process 4. Both auto-restart on Pi startup via rc.local 5. Killing one does not crash the other | Medium | 3 | To Do |  | Use & to background display. Consider systemd service later
Sprint 5 - Goal: Custom PCB designed in EasyEDA and ordered from JLCPCB
US-028 | EP-07 | Sprint 5 | Set Up EasyEDA Project | Hardware Engineer | create an EasyEDA project with all ARIA components in the library | I can start drawing the schematic with verified component symbols | 1. EasyEDA account created at easyeda.com 2. Project ARIA_Bot_PCB created 3. New schematic created in project 4. L298N LM2596 PAM8403 found in library with footprints 5. 40-pin Pi header found 6. All LCSC part numbers noted | High | 3 | To Do |  | Only start PCB design after all 5 robot build weeks are complete
US-029 | EP-07 | Sprint 5 | Draw Power Section Schematic | Hardware Engineer | draw the complete power supply section of the ARIA PCB schematic | the schematic accurately shows how LiPo battery powers all components | 1. XT60 battery connector placed 2. SPDT power switch placed 3. LM2596 number 1 circuit complete for Pi 5V 4. LM2596 number 2 circuit complete for Arduino 5V 5. Battery voltage divider placed for Arduino A0 6. All decoupling caps placed on IC power pins 7. ERC passes with 0 errors | High | 8 | To Do |  | Check LM2596 datasheet for correct inductor and capacitor values
US-030 | EP-07 | Sprint 5 | Draw Motor Driver Schematic | Hardware Engineer | draw both L298N motor driver circuits in the schematic | the schematic shows exactly how the Arduino controls all 4 motors | 1. L298N number 1 complete controls Left motors 2. L298N number 2 complete controls Right motors 3. All 8 back-EMF diodes 1N4007 placed correctly 4. 8 motor output screw terminals placed 5. All Arduino motor control pins labelled 6. Decoupling caps on all L298N power pins | High | 8 | To Do |  | 4 diodes per L298N chip are critical - motor spikes destroy the chip without them
US-031 | EP-07 | Sprint 5 | Complete PCB Layout and Order | Hardware Engineer | complete the full PCB layout and order 5 boards from JLCPCB | a professionally manufactured PCB arrives ready for soldering | 1. Board outline 120mm x 100mm 2. 4 mounting holes in corners 3.2mm diameter 3. Power traces minimum 40 mil width 4. Signal traces minimum 6 mil width 5. Ground plane copper pour on Layer 2 6. DRC passes with 0 errors 7. Gerber files exported as zip 8. Order placed on JLCPCB 5 boards 4-layer 9. Order confirmation email received | Medium | 13 | To Do |  | Estimated cost 5 boards plus shipping approximately 35 dollars total
TOTAL: 31 User Stories ¦ Story Points: 140 ¦ 5 Sprints

## Sprint 1
Sprint 1 ¦ Weeks 1-2 ¦ Goal: Robot assembled and powered on. Pi running with all software installed
To Do (8) | In Progress (0) | Done (0) | Blocked (0)
US-001 ¦ High ¦ 3 pts
Assemble Robot Chassis
As a Robot Builder, I want to assemble the 4WD chassis with all 4 motors attached...
US-002 ¦ High ¦ 2 pts
Mount Pi and Arduino
As a Robot Builder, I want to mount Raspberry Pi 4 and Arduino Mega on the top platform...
US-003 ¦ Critical ¦ 5 pts
Connect Power System
As a Robot Builder, I want to wire LiPo battery through buck converters to Pi and Arduino...
US-004 ¦ High ¦ 2 pts
Mount Ultrasonic Sensors
As a Robot Builder, I want to mount 3 HC-SR04 sensors at front left and right of robot...
US-005 ¦ Critical ¦ 2 pts
Flash Raspberry Pi OS
As a Developer, I want to flash Raspberry Pi OS 64-bit to the 32GB SD card...
US-006 ¦ Critical ¦ 3 pts
Install Python Dependencies
As a Developer, I want to install all required Python libraries on the Raspberry Pi...
US-007 ¦ Critical ¦ 2 pts
Configure OpenAI API
As a Developer, I want to set up and verify the OpenAI API connection...
US-008 ¦ High ¦ 3 pts
Verify Pi-Arduino Serial Link
As a Developer, I want to confirm Raspberry Pi can communicate with Arduino via USB se...

## Sprint 2
Sprint 2 ¦ Weeks 2-3 ¦ Goal: All 4 wheels controlled by Pi commands. All 3 sensors streaming data
To Do (9) | In Progress (0) | Done (0) | Blocked (0)
US-009 ¦ Critical ¦ 5 pts
Wire L298N Motor Drivers
As a Developer, I want to wire both L298N motor drivers to the Arduino Mega and motors...
US-010 ¦ Critical ¦ 3 pts
Upload Motor Test Code
As a Developer, I want to upload the motor test sketch to Arduino and verify each whee...
US-011 ¦ Critical ¦ 5 pts
Full Motor Command System
As a Developer, I want to upload full Arduino code that accepts serial commands from P...
US-012 ¦ High ¦ 3 pts
Test Motor Commands from Pi
As a Developer, I want to run the Python motor test script from the Raspberry Pi...
US-013 ¦ Medium ¦ 2 pts
Smooth Speed Control
As a Developer, I want to implement speed levels slow normal fast turbo for movement...
US-014 ¦ High ¦ 3 pts
Wire HC-SR04 Sensors
As a Developer, I want to wire all 3 HC-SR04 ultrasonic sensors to the Arduino Mega...
US-015 ¦ High ¦ 5 pts
Sensor Data Streaming
As a Developer, I want to have the Arduino continuously send sensor readings to the Pi...
US-016 ¦ High ¦ 5 pts
Obstacle Avoidance Logic
As a Developer, I want to have ARIA automatically stop when obstacle is within 20cm...
US-017 ¦ Medium ¦ 2 pts
Sensor Scan Command
As a Developer, I want to have ARIA report sensor distances when asked to scan...

## Sprint 3
Sprint 3 ¦ Week 4 ¦ Goal: ARIA listens to voice, understands GPT-4 commands, moves and speaks responses
To Do (6) | In Progress (0) | Done (0) | Blocked (0)
US-018 ¦ Critical ¦ 3 pts
Set Up Microphone Input
As a Developer, I want to connect and configure the ReSpeaker 2-Mic HAT for voice capt...
US-019 ¦ Critical ¦ 5 pts
Integrate Whisper STT
As a Developer, I want to have Whisper convert recorded audio to text locally on the P...
US-020 ¦ Critical ¦ 8 pts
Implement GPT-4 AI Agent
As a Developer, I want to have GPT-4 interpret voice commands and decide robot actions...
US-021 ¦ High ¦ 5 pts
Voice Command Loop
As a Developer, I want to have ARIA continuously listen understand and act in a loop...
US-022 ¦ High ¦ 3 pts
Text-to-Speech Output
As a Developer, I want to have ARIA speak responses out loud using the connected speak...
US-023 ¦ Low ¦ 8 pts
Wake Word Detection
As a Developer, I want to have ARIA only respond when I say Hey ARIA first...

## Sprint 4
Sprint 4 ¦ Week 5 ¦ Goal: Display shows animated face and live telemetry. All systems running together
To Do (4) | In Progress (0) | Done (0) | Blocked (0)
US-024 ¦ High ¦ 5 pts
Connect TFT Display
As a Developer, I want to connect the 3.5 inch TFT display to the Raspberry Pi via SPI...
US-025 ¦ High ¦ 8 pts
ARIA Animated Face
As a Developer, I want to have the display show animated eyes that react to ARIA curre...
US-026 ¦ Medium ¦ 5 pts
Live Telemetry Display
As a Developer, I want to have the display show live data alongside the animated face...
US-027 ¦ Medium ¦ 3 pts
Run Display and Brain Together
As a Developer, I want to have aria_display.py and aria_brain.py run simultaneously on...

## Sprint 5
Sprint 5 ¦ Post-Build ¦ Goal: Custom PCB designed in EasyEDA and ordered from JLCPCB
To Do (4) | In Progress (0) | Done (0) | Blocked (0)
US-028 ¦ High ¦ 3 pts
Set Up EasyEDA Project
As a Hardware Engineer, I want to create an EasyEDA project with all ARIA components in the li...
US-029 ¦ High ¦ 8 pts
Draw Power Section Schematic
As a Hardware Engineer, I want to draw the complete power supply section of the ARIA PCB schem...
US-030 ¦ High ¦ 8 pts
Draw Motor Driver Schematic
As a Hardware Engineer, I want to draw both L298N motor driver circuits in the schematic...
US-031 ¦ Medium ¦ 13 pts
Complete PCB Layout and Order
As a Hardware Engineer, I want to complete the full PCB layout and order 5 boards from JLCPCB...

## Definition of Done
ARIA BOT - DEFINITION OF DONE (DoD)
A user story is DONE only when ALL items in its category are checked off
Hardware Stories
Physical | All components physically secured - no loose wires or parts | Not Checked
Power | All voltage levels verified with multimeter before powering on | Not Checked
Tested | Component tested in isolation before full integration | Not Checked
Safe | No short circuits detected on any power rails | Not Checked
Documented | All wiring connections noted and match the build guide | Not Checked
Software Stories
Code | Code runs without any errors or exceptions | Not Checked
Tested | Feature tested with at least 5 different inputs or commands | Not Checked
Error Handling | All errors caught and robot responds gracefully without crashing | Not Checked
Saved | Code saved to a clearly named file on the Raspberry Pi | Not Checked
Comments | Comments added to explain any complex code sections | Not Checked
Integration Stories
End-to-End | Feature works as part of the full ARIA system not just in isolation | Not Checked
Performance | Response time meets the requirement stated in acceptance criteria | Not Checked
Voice Tested | Voice command tested with at least 3 different phrasings | Not Checked
No Regression | Previously working features still work after this story is done | Not Checked
Demo Ready | Feature can be successfully demonstrated to another person | Not Checked